## Sheet1
	March			April
	10-16	17-23	24-30	31-6	7-13	13-20	21-28

LOW	Access Aurora
		Understand Current Testing Methodologies
			Develop Aurora Benchmarking tests
MEDIUM	Access Aurora and Learned Current Testing Methodologies			Begin Running Tests
		Begin Benchmarking and determine bottlenecks			Benchmark and determine Bottlenecks
		Find/Develop barebones database model	Find/Develop barebones database model			Theorize Potential improvements
			Devise new DDL approach	Implement new DDL approach			Clean Up
					Implement new DDL approach
						Bug Fixes/Modifications
						Complete prototype
							Clean Up
HIGH	Access Aurora and Learned Current Testing Methodologies	Begin Benchmarking and determine bottlenecks
		Find/Develop barebones database model
		Devise new DDL approach
			Implement control DDL approach
			Implement new DDL approach	Implement control DDL approach
				Implement new DDL approach
					Bug Fixes/Modifications
					Complete prototype
						Benchmark both prototypes
							Clean Up